## Slide 1: THIRD MEETING OF THE COMMITTEE FOR RECOMMENDATIONS & ADOPTION OF BEST PRACTICES FOR UPCOMING POPULATION CENSUS 27.04.2021
MINISTRY OF PLANNING, DEVELOPMENT & SPECIAL INITIATIVES

## Slide 2
AGENDA OF THE MEETING
Implementation status of decisions of previous meeting
Draft outlines for the proposed report
Discussion on comprehensive work plan & constitution of working groups
Presentation on Digital Census
Any other item with the permission of the Chair.
Notes: 2
2

## Slide 3
IMPLEMENTATION STATUS OF DECISIONS OF PREVIOUS MEETING
Decision:
  Reports prepared by PBS on key issues raised may be shared with all members for their input and guidance.
Status:
All material prepared based on :
Minutes of the Sub- Committee of the Governing Council
International / National observer reports
Technical Committees of the Provinces
Press Clipping and PBS replies
Technical Evaluation Report
Sent to all the respectable members on 14.04.2021
Notes: 3
3

## Slide 4
IMPLEMENTATION STATUS OF DECISIONS OF PREVIOUS MEETING
Decision:
  Comprehensive work plan would be formulated along with constitution of working groups with Terms of reference and specific timelines on each TOR of the committee.
Status:
PBS has started in house working on each TOR, however proposed the Members from the Committee.
PBS prepared comprehensive work plan with specific timelines to complete task timely.
Notes: 4
4

## Slide 5
IMPLEMENTATION STATUS OF DECISIONS OF PREVIOUS MEETING
Decision:
  Identify themes and prepare outlines for the proposed report for presenting to committee
Status:
PBS prepared main outline of the Report and five outlines of the each TOR
Main outline
Outline of the TOR-2
Outline of the TOR-3
Outline of the TOR-4
Outline of the TOR-5
Notes: 5
5

## Slide 6
IMPLEMENTATION STATUS OF DECISIONS OF PREVIOUS MEETING
Decision:
  Robust communication strategy must be developed for reducing gaps and build confidence of all stakeholders.
Status:
Noted for compliance and work has been started.
Notes: 6
6

## Slide 7
IMPLEMENTATION STATUS OF DECISIONS OF PREVIOUS MEETING
Decision:
  Digital technology must be adopted for next census in line with the experiences countries which already used different digital tools/platforms and innovative hybrid enumeration methods
Status:
Initial work has been started. Brief overview given in presentation
Notes: 7
7

## Slide 8
IMPLEMENTATION STATUS OF DECISIONS OF PREVIOUS MEETING
Decision:
  Mechanism for involvement of Provincial Governments / Academia in the whole census process for its wider acceptably and ownership may also be devised.
Status:
Noted for compliance;
Notes: 8
8

## Slide 9
THANK YOU