## Slide 1: To Review the Best Practices of Field Operations Including Monitoring/supervision to Minimize the Omission/Errors and Complete Coverage
MINISTRY OF PLANNING, DEVELOPMENT
& SPECIAL INITIATIVES
Dated: 25-06-2021

## Slide 2
Delayed publicity campaign.
No involvement of local levels for appropriate delivery of objective.
Minimal use of social media
Due to rapid growth of population, issues regarding block size was faced. Maps were not available / updated. Overlapping of Blocks
Block Up dation
/ Maps
Pilot Census
Pilot Census was not conducted
Confidence/ Trust Deficit
Controversies generated due to lack of involvement of all stakeholders in whole census process (especially Provinces / Political Parties in data compilation process)
Comprehensive Review of 2017 Census and Issues Faced
Clarity about Census Objectives
General public was not fully aware about true census objectives and importance
Definitions were not clear and issues regarding identification of usual place of residence faced.
Trainings were not comprehensive and non usage of modern technologies
No proper mechanism for evaluation of trainings
Trainings
Census Communication Strategy
2

## Slide 3
To address these issues and ownership of Census process, following are required
Prudent Planning
Broder Involvement of stakeholders
Affective Methodology/ Modern Techniques
No proper mechanism designed to evaluate FQCs forms
Modern monitoring Techniques were not used
Real time monitoring was not carried out
Army was involved in parallel data collection. Against International Laws/UN principles
Phases
CNIC/
Confidentiality
Involvement of Army in Data Collection
Monitoring
Evaluation
Overlapping issues .
Double counting due movement of population.
Verification of CNIC from NADRA created controversies may have led to under counting of population
Comprehensive Review of 2017 Census and Issues Faced
Post Enumeration Survey not conducted
  Ineffective role of Provincial Committees
Weak / sluggish coordination / Reporting Mechanism with District management .
Committees performance was not adequate and unable to fully achieve objectives
3
Due to conventional method of enumeration issues regarding instant changes in questionnaire was not communicated properly

## Slide 4
Country | BANGLADESH 2021 | INDIA 2021 | IRAN 2016 | PAKISTAN 2017
Planning | 2 years | 2 years | 5 years | Since 2008
Periodicity | Ten Years | Ten Years | five years | Ten years
Pilot Survey | √ | √ | √ | 
Method of Enumeration | De- jure | De- jure | De- jure | De- jure
Frame Hierarchy | Country, Divisions, Districts , City Corporations ,upazilas | Country , Province , Districts ,Sub District/ Tehsil/ Talukas , Villages | Province, Sub-province City/ Urban area, Rural ,Village, Avenue, Street, Floor/ Apartment, Postal code, Household’s fixed, telephone number | Province, Division, Admin District, Census District/Tehsil, Charge, Circle, Block
Enumeration Areas/blocks | 4,00,000/120 houses | 2,500,000/150-180 houses | 95,192/100 houses | 168,943/200-250 houses
Digitize Maps | √ | Blocks Boundaries formation/ frame updations completed one year before the census | √ | Digital (urban) and manual Map (rural).Updation of urban completed in 2013 and rural blocks was initiated in 2015 but not completed
REVIEW OF REGIONAL COUNTRIES- FIELD OPERATION MECHANISM
7

## Slide 5
Country | BANGLADESH 2021 | INDIA 2021 | IRAN 2016 | PAKISTAN 2017
Involvement of Stakeholders | Digitization of documentation of Census reports The expert committee decided for the census in consultation with the experts and stakeholders. | The data users’ conference with various stakeholders( Central ministries, state governments, academic institutions and International Organizations ) | All stakeholders were involved | Key stakeholder were involved International workshop for whole census process July 2016
Trainers | 470,000 | 98 National Trainer, 1800 master trainers 43,500 field trainers, 30 lac enumerators | 324 Master Trainers 3500 trainers 22,000 enumerators | Master Trainers – 65 Trainers – 700 120,000 field staff
Modern Technology for Training | √ | √ Enumerator will use own devices | √ 47% data collection through internet(self enumeration) | Manual using ICR Forms
Staff | Teachers | Teachers | Diploma, degree holder staff, Male: 57%, Female : 43% | Teachers (2% Female)
Monitoring /Web portal | √ | √ | √ | 
Post Evaluation | √ | √ | √ | 
REVIEW OF REGIONAL COUNTRIES- FIELD OPERATION MECHANISM

## Slide 6
REVIEW OF DEVELOPED COUNTRIES- FIELD OPERATION MECHANISM |  |  | 
Country | USA April 2020 | UK (2021 Postponed) | Australia, August 2021
Planning | 2015-2020 | 2015-2020 | 6 years/before releasing 2016
Frequency | Ten Years | Ten Years | Five years
Method | Use satellite and GPS imagery in 2020 census to identify areas with changes Verification of those addresses in person. | An invitation to complete the form online providing a unique access code (UAC) and website address. | Unique id code sent to household for self enumeration .
Online & Paper | √ | √ | √
Field Work | Internet based, For non response and areas without internet access paper based questionnaire were sent | Internet based Sign Language questionnaire used as well | Internet based, For non response and areas without internet access paper based questionnaire were sent
Staff | Hired temporary and part time workers Retirees, College students job less Flexible working hours include days/ evenings/ weekends. | Any one can register online and training | Hiring 30,000 field staff, online registration and training
Technology | Census takers use secure smartphones Special software is designed to optimize assignments, and real time monitoring software was used to avoid multiple responses for the same person across census records | Online application, Dashboards | OCT 2020 pretest 0.1 million household A separate Data Operations Centre will process the information collected from all digital and paper Census forms.
PES & Demographic Analysis | Results will be release in Nov 2021 Est. sample size= 10 050 blocks | √ | PES sample size 2011= 40,000 households
9

## Slide 7
Main Considerations …
Methodology & Confidence Building Measures
Ensure Universality : Counting of whole population residing in country at time of census irrespective of it Status/ Holder of CNIC or not
Clarity regarding the Primary objective of Census (Policy Planning Purposes) for awareness of General Public
Census may be conducted “Digitally” with Real time monitoring
Census must be conducted simultaneously in shortest possible time
Notes: 7
7

## Slide 8
Methodology & Confidence Building Measures
  For Ownership of Process & Results: Engagement of all stakeholders:-
  Provincial Governments, Elected representatives Notables & Academia etc.
For Proper Coordination, Effective Monitoring, Credibility and Ownership of whole census process , Census Command & Control Center (model of NCOC) may be established
Clearly define methodology : De-jure/ De-facto
Adoption of UN guidelines by aligning them to ground realities
Do not link/ cross check any data with NADRA
Main Considerations …
Notes: 8
8

## Slide 9
Main Considerations …
Field Operations:
Exhaustive Frame for Complete Coverage
Availability of Updated and Digitized maps
Ensure Conduct of Pilot Survey
Main Census form should be short, relevance to objective of Census
Detailed questionnaire on key sectors should be on Sample basis
  Along with Teachers & Revenue staff, option of using LHWs may be considered
  Number of female enumerators will be Increased
  Development of Census Support Centers at tehsil level for effective coordination, monitoring and IT Support
  Block Size.xlsx
Notes: 9
9

## Slide 10
Main Considerations …
Field Operations:
  Geo tagging of all structures for Complete Coverage and robust Monitoring & Evaluation
  Public Campaign has to begin early and extend right up to the release of the first initial results
  Communication Strategy with involvement of locals, Minbar/masjid, Hujra/ Bhaitak etc.
Comprehensive trainings by adopting Digital Interventions with sufficient time at each level.
Ensure conduct of Post Enumeration Survey for Quality & Coverage Evaluation
Notes: 10
10

## Slide 11
THANK YOU

## Slide 12
Census Command & Operation Centre (CCOC)
Minister, PD&SI
Chief Minister, Punjab
Chief Minister, Sindh
Chief Minister, Balochistan
Chief Minister, KP
Chief Minister, GB
Chief Minister, AJ&K
Chief Secretary, AJ&K
Chief Secretary, GB
Forum for Oversee Coordination and Management of Census and Policy decisions
Chief Census Commissioner
Chief Secretary,
Punjab
Chief Secretary,
Sindh
Chief Secretary, KP
Chief Secretary Balochistan
Provincial Census Commissioner (PBS)
Commissioner (Divisional Census Commissioner)
Deputy Commissioner
Census District Officer
(Assistant Census Commissioner )
Coordination and Management of Census in the province
Video Wall Monitoring through Dashboard for real time monitoring and rectification by using CATI approach
Weekly meetings will be conducted
Divisional Census Commissioner
Census Support Center
Deputy Commissioner
Census Support Center
Notes: 12
12

## Slide 13: UN Principles/Guidelines
Agreement and Engagement of Public: is required for awareness, Participation and ownership
Individual enumeration - information on each enumerated person
Simultaneity - unique and well defined reference period
Universality – Count every person residing and/or present in the country at a defined singular point in time.
Small area data - data on the number and characteristics of the population and housing related to the smallest geographic areas of the country, with confidentiality
Defined periodicity - the census should be taken at regular intervals (5 or 10 years).

## Slide 14: UN Principles/Guidelines
Training- Guides/manuals in local Languages, by using innovative technology
Monitoring –Effective System to monitor the progress of the operation for correction of errors and to make necessary adjustments in the course of the fieldwork
Evaluation- Post Enumeration Survey and Demographic Analysis.
Register Based Census is the cost affective and modern technique but in the context of Pakistan due to non availability of registers cannot be considered for upcoming census